## 工数予実管理表
プロジェクト名 |  | Amateur Programmers | [16 empty] | 開始日 |  |  |  | 2023-06-01
[19 empty] | 終了日 |  |  |  | 2023-06-30
No | タスク | [7 empty] | 担当者 |  |  | 予定 |  | ステータス |  |  |  |  | 2023-06-01
| カテゴリ | 作業名 | ファイル形式 | [8 empty] | 開始日 | 終了日 |  |  |  | 工数 | 進捗率 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | ステータス | 進捗率
[19 empty] | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 完了 | 100% | 進捗率
| プログラミング | [47 empty] | 未着手 | 0% | 100%
| jsp | [47 empty] | 1% | 1% | 0%
|  | ホーム画面用 | Home.jsp | [5 empty] | 勝又 |  |  | 2023-06-13 | 2023-06-13 | 完了 |  |  | 1 | 100% | [30 empty] | 2% | 2% | bar: 火
|  | ログイン画面用 | Login.jsp | [5 empty] | 斎藤 |  |  | 2023-06-13 | 2023-06-13 | 完了 |  |  | 1 | 100% | [30 empty] | 3% | 3% | bar: 火
|  | 新規登録画面用 | Account.jsp | [5 empty] | 斎藤 |  |  | 2023-06-13 | 2023-06-13 | 完了 |  |  | 1 | 100% | [30 empty] | 4% | 4% | bar: 火
|  | １日のスケジュール用 | Schedule.jsp | [5 empty] | 鈴木 |  |  | 2023-06-12 | 2023-06-13 | 完了 |  |  | 2 | 100% | [30 empty] | 5% | 5% | bar: 月 to 火
|  | カレンダー画面用 | Calendar.jsp | [5 empty] | 勝又 |  |  | 2023-06-12 | 2023-06-13 | 完了 |  |  | 2 | 100% | [30 empty] | 6% | 6% | bar: 月 to 火
|  | 目標入力画面用 | GoalRegist.jsp | [5 empty] | 篠崎 |  |  | 2023-06-12 | 2023-06-13 | 完了 |  |  | 2 | 100% | [30 empty] | 7% | 7% | bar: 月 to 火
|  | タスク記入画面用 | TaskRegist.jsp | [5 empty] | 篠崎 |  |  | 2023-06-12 | 2023-06-13 | 完了 |  |  | 2 | 100% | [30 empty] | 8% | 8% | bar: 月 to 火
|  | 達成度入力表示用 | Achieve.jsp | [5 empty] | 斎藤 |  |  | 2023-06-12 | 2023-06-13 | 完了 |  |  | 2 | 100% | [30 empty] | 9% | 9% | bar: 月 to 火
|  | 説明画面用 | Explanation.jsp | [5 empty] | 勝又 |  |  | 2023-06-13 | 2023-06-13 | 完了 |  |  | 1 | 100% | [30 empty] | 10% | 10% | bar: 火
| 新規追加 | Todo画面用 | TodoRejist.jsp | [5 empty] | 篠崎 |  |  | 2023-06-15 | 2023-06-16 | 完了 |  |  | 2 | 100% | [30 empty] | 11% | 11% | bar: 木 to 金
| 新規追加 | ID表示用 | AccountID.jsp | [5 empty] | 鈴木 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 12% | 12% | bar: 金
|  | Idｐｗ用 | IdpwDao.java | [5 empty] | 永田 |  |  | 2023-06-12 | 2023-06-12 | 完了 |  |  | 1 | 100% | [30 empty] | 13% | 13% | bar: 月
|  | 日付データ用 | DaysDao.java | [5 empty] | 永田 |  |  | 2023-06-12 | 2023-06-12 | 完了 |  |  | 1 | 100% | [30 empty] | 14% | 14% | bar: 月
|  | ログインデータ用 | LgDao.java | [5 empty] | 永田 |  |  | 2023-06-14 | 2023-06-14 | 完了 |  |  | 1 | 100% | [30 empty] | 15% | 15% | bar: 水
|  | 短期目標データ用 | SgDao.java | [5 empty] | 永田 |  |  | 2023-06-15 | 2023-06-15 | 完了 |  |  | 1 | 100% | [30 empty] | 16% | 16% | bar: 木
|  | Todoデータベース用 | TodotbDao.java | [5 empty] | 永田 |  |  | 2023-06-15 | 2023-06-15 | 50% |  |  | 1 | 50% | [30 empty] | 17% | 17% | bar: 木
|  | タスクデータ用 | TasktbDao.java | [5 empty] | 永田 |  |  | 2023-06-14 | 2023-06-14 | 完了 |  |  | 1 | 100% | [30 empty] | 18% | 18% | bar: 水
|  | 月データ用 | MemotbDao.java | [5 empty] | 永田 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 19% | 19% | bar: 金
|  | ＩＤｐｗ用 | Idpw.java | [5 empty] | 篠崎 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 20% | 20% | bar: 月
|  | 日付データ用 | Days.java | [5 empty] | 篠崎 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 21% | 21% | bar: 月
|  | ログインデータ用 | Lg.java | [5 empty] | 勝又 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 22% | 22% | bar: 月
|  | 短期目標データ用 | Sg.java | [5 empty] | 勝又 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 23% | 23% | bar: 月
|  | Todo画面用 | Todo.java | [5 empty] | 鈴木 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 24% | 24% | bar: 月
|  | タスク画面用 | Task.java | [5 empty] | 鈴木 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 25% | 25% | bar: 月
|  | メモ画面用 | Memo.java | [5 empty] | 斎藤 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 26% | 26% | bar: 月
|  | ユーザー画面用 | User.java | [5 empty] | 斎藤 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 27% | 27% | bar: 月
|  | 達成度入力画面用 | Achieve.java | [5 empty] | 永田 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 28% | 28% | bar: 月
|  | 結果表示画面用 | Result.java | [5 empty] | 永田 |  |  | 2023-06-16 | 2023-06-16 | 完了 |  |  | 1 | 100% | [30 empty] | 29% | 29% | bar: 月
|  | ホーム画面用 | HomeServlet.java | [5 empty] | 斎藤 |  |  | 2023-06-19 | 2023-06-21 | 未着手 |  |  | 3 | 0% | [30 empty] | 30% | 30% | bar: 月 to 水
|  | ログイン画面用 | LoginServlet.java | [5 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 | 完了 |  |  | 3 | 100% | [30 empty] | 31% | 31% | bar: 月 to 水
|  | アカウント画面用 | AccountServlet.java | [5 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 | 完了 |  |  | 3 | 100% | [30 empty] | 32% | 32% | bar: 月 to 水
|  | １日のスケジュール画面用 | ScheduleServlet.java | [5 empty] | 鈴木 |  |  | 2023-06-19 | 2023-06-21 | 完了 |  |  | 3 | 100% | [30 empty] | 33% | 33% | bar: 月 to 水
|  | カレンダー画面用 | CalendarServlet.java | [5 empty] | 斎藤 |  |  | 2023-06-14 | 2023-06-16 | 80% |  |  | 3 | 80% | [30 empty] | 34% | 34% | bar: 水 to 金
|  | 目標入力画面用 | GoalRegistServlet.java | [5 empty] | 篠崎 |  |  | 2023-06-19 | 2023-06-21 | 完了 |  |  | 3 | 100% | [30 empty] | 35% | 35% | bar: 月 to 水
|  | タスク画面用 | TaskRegistServlet.java | [5 empty] | 篠崎 |  |  | 2023-06-19 | 2023-06-21 | 未着手 |  |  | 3 | 0% | [30 empty] | 36% | 36% | bar: 月 to 水
|  | 達成度画面用 | AchieveServlet.java | [5 empty] | 斎藤 |  |  | 2023-06-19 | 2023-06-21 | 50% |  |  | 3 | 50% | [30 empty] | 37% | 37% | bar: 月 to 水
|  | 説明画面用 | ExplanationServlet.java | [5 empty] | 勝又 |  |  | 2023-06-19 | 2023-06-21 | 完了 |  |  | 3 | 100% | [30 empty] | 38% | 38% | bar: 月 to 水
| 新規追加 | 次月画面用 | NextMonthServlet.java | [5 empty] | 斎藤 |  |  | 2023-06-14 | 2023-06-16 | 80% |  |  | 6 | 80% | [30 empty] | 39% | 39% | bar: 水 to 金; 月 to 水
| 新規追加 | 前月画面用 | LastMonthServlet.java | [5 empty] | 斎藤 |  |  | 2023-06-14 | 2023-06-16 | 80% |  |  | 6 | 80% | [30 empty] | 40% | 40% | bar: 水 to 金; 月 to 水
|  | 共通部分用 | common.js | [5 empty] | 勝又 |  |  | 2023-06-20 | 2023-06-23 | 未着手 |  |  | 4 | 0% | [30 empty] | 41% | 41% | bar: 火 to 金
|  | ホーム画面用 | home.js | [5 empty] | 勝又 |  |  | 2023-06-15 | 2023-06-23 | 未着手 |  |  | 7 | 0% | [30 empty] | 42% | 42% | bar: 木 to 金; 月 to 金
|  | ログイン画面用 | login.js | [5 empty] | 鈴木 |  |  | 2023-06-15 | 2023-06-23 | 完了 |  |  | 7 | 100% | [30 empty] | 43% | 43% | bar: 木 to 金; 月 to 金
|  | アカウント画面用 | account.js | [5 empty] | 鈴木 |  |  | 2023-06-15 | 2023-06-23 | 完了 |  |  | 7 | 100% | [30 empty] | 44% | 44% | bar: 木 to 金; 月 to 金
|  | １日のスケジュール画面用 | schedule.js | [5 empty] | 鈴木 |  |  | 2023-06-12 | 2023-06-23 | 完了 |  |  | 10 | 100% | [30 empty] | 45% | 45% | bar: 月 to 金; 月 to 金
|  | カレンダー画面用 | calendar.js | [5 empty] | 斎藤 |  |  | 2023-06-15 | 2023-06-23 | 未着手 |  |  | 7 | 0% | [30 empty] | 46% | 46% | bar: 木 to 金; 月 to 金
|  | 目標入力画面用 | goal_regist.js | [5 empty] | 篠崎 |  |  | 2023-06-12 | 2023-06-23 | 80% |  |  | 10 | 80% | [30 empty] | 47% | 47% | bar: 月 to 金; 月 to 金
|  | タスク入力画面用 | task_regist.js | [5 empty] | 篠崎 |  |  | 2023-06-12 | 2023-06-23 | 70% |  |  | 10 | 70% | [30 empty] | 48% | 48% | bar: 月 to 金; 月 to 金
|  | 達成度画面用 | achieve.js | [5 empty] | 斎藤 |  |  | 2023-06-15 | 2023-06-23 | 未着手 |  |  | 7 | 0% | [30 empty] | 49% | 49% | bar: 木 to 金; 月 to 金
|  | 説明画面用 | explanation.js | [5 empty] | 勝又 |  |  | 2023-06-13 | 2023-06-23 | 90% |  |  | 7 | 90% | [30 empty] | 50% | 50% | bar: 月 to 金; 月 to 金
| 新規追加 | todo画面用 | todo_regist.js | [5 empty] | 篠崎 |  |  | 2023-06-15 | 2023-06-23 | 完了 |  |  | 7 | 100% | [30 empty] | 51% | 51% | bar: 木 to 金; 月 to 金
|  | 共通部分画面用 | common.css | [5 empty] | 勝又 |  |  | 2023-06-20 | 2023-06-23 | 90% |  |  | 4 | 90% | [30 empty] | 52% | 52% | bar: 火 to 金
|  | ホーム画面用 | home.css | [5 empty] | 勝又 |  |  | 2023-06-14 | 2023-06-23 | 70% |  |  | 8 | 70% | [30 empty] | 53% | 53% | bar: 水 to 金; 月 to 金
|  | ログイン画面用 | login.css | [5 empty] | 斎藤 |  |  | 2023-06-16 | 2023-06-23 | 完了 |  |  | 6 | 100% | [30 empty] | 54% | 54% | bar: 金; 月 to 金
|  | アカウント画面用 | account.css | [5 empty] | 斎藤 |  |  | 2023-06-16 | 2023-06-23 | 完了 |  |  | 6 | 100% | [30 empty] | 55% | 55% | bar: 金; 月 to 金
|  | １日のスケジュール用 | schedule.css | [5 empty] | 鈴木 |  |  | 2023-06-14 | 2023-06-23 | 80% |  |  | 8 | 80% | [30 empty] | 56% | 56% | bar: 水 to 金; 月 to 金
|  | カレンダー画面用 | calendar.css | [5 empty] | 斎藤 |  |  | 2023-06-15 | 2023-06-23 | 70% |  |  | 7 | 70% | [30 empty] | 57% | 57% | bar: 木 to 金; 月 to 金
|  | 目標達成画面用 | goal_regist.css | [5 empty] | 篠崎 |  |  | 2023-06-15 | 2023-06-23 | 未着手 |  |  | 7 | 0% | [30 empty] | 58% | 58% | bar: 木 to 金; 月 to 金
|  | タスク入力画面用 | task_regist.css | [5 empty] | 篠崎 |  |  | 2023-06-15 | 2023-06-23 | 未着手 | 未着手 | 未着手 | 7 | 0% | [30 empty] | 59% | 59% | bar: 木 to 金; 月 to 金
|  | 達成度画面用 | achieve.css | [5 empty] | 斎藤 |  |  | 2023-06-19 | 2023-06-23 | 未着手 | 未着手 | 未着手 | 5 | 0% | [30 empty] | 60% | 60% | bar: 月 to 金
| 新規追加 | todo画面用 | todo_regist.css | [5 empty] | 勝又 |  |  | 2023-06-14 | 2023-06-23 | 未着手 |  |  | 8 | 0% | [30 empty] | 61% | 61% | bar: 水 to 金; 月 to 金
| 新規追加 | 新規登録ID表示画面用 | AccountID.css | [5 empty] | 鈴木 |  |  | 2023-06-14 | 2023-06-23 | 60% |  |  | 8 | 60% | [30 empty] | 62% | 62% | bar: 水 to 金; 月 to 金
| 単体テスト | Home.jsp |  | Home.jsp | Home.jsp | Home.jsp | Home.jsp | Home.jsp | 勝又 | 勝又 | 勝又 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 63% | 63% | bar: 月
|  | Login.jsp |  | Login.jsp | Login.jsp | Login.jsp | Login.jsp | Login.jsp | 斎藤 | 斎藤 | 斎藤 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 64% | 64% | bar: 月
|  | Account.jsp |  | Account.jsp | Account.jsp | Account.jsp | Account.jsp | Account.jsp | 斎藤 | 斎藤 | 斎藤 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 65% | 65% | bar: 月
|  | Schedule.jsp |  | Schedule.jsp | Schedule.jsp | Schedule.jsp | Schedule.jsp | Schedule.jsp | 鈴木 | 鈴木 | 鈴木 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 66% | 66% | bar: 月
|  | Calendar.jsp |  | Calendar.jsp | Calendar.jsp | Calendar.jsp | Calendar.jsp | Calendar.jsp | 斎藤 | 勝又 | 勝又 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 67% | 67% | bar: 月
|  | GoalRegist.jsp |  | GoalRegist.jsp | GoalRegist.jsp | GoalRegist.jsp | GoalRegist.jsp | GoalRegist.jsp | 篠崎 | 篠崎 | 篠崎 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 68% | 68% | bar: 月
|  | TaskRegist.jsp |  | TaskRegist.jsp | TaskRegist.jsp | TaskRegist.jsp | TaskRegist.jsp | TaskRegist.jsp | 篠崎 | 篠崎 | 篠崎 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 69% | 69% | bar: 月
|  | Achieve.jsp |  | Achieve.jsp | Achieve.jsp | Achieve.jsp | Achieve.jsp | Achieve.jsp | 斎藤 | 斎藤 | 斎藤 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 70% | 70% | bar: 月
|  | Explanation.jsp |  | Explanation.jsp | Explanation.jsp | Explanation.jsp | Explanation.jsp | Explanation.jsp | 勝又 | 勝又 | 勝又 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 71% | 71% | bar: 月
|  | TodoRejist.jsp |  | TodoRejist.jsp | TodoRejist.jsp | TodoRejist.jsp | TodoRejist.jsp | TodoRejist.jsp | 篠崎 | 篠崎 | 篠崎 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 72% | 72% | bar: 月
|  | AccountID.jsp |  | AccountID.jsp | AccountID.jsp | AccountID.jsp | AccountID.jsp | AccountID.jsp | 鈴木 | 鈴木 | 鈴木 | 2023-06-26 | 2023-06-26 |  |  |  | 1 | [31 empty] | 73% | 73% | bar: 月
|  | IdpwDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 74% | 74% | bar: 月 to 水
|  | DaysDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 75% | 75% | bar: 月 to 水
|  | LgDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 76% | 76% | bar: 月 to 水
|  | SgDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 77% | 77% | bar: 月 to 水
|  | TodotbDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 78% | 78% | bar: 月 to 水
|  | TasktbDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 79% | 79% | bar: 月 to 水
|  | MemotbDao.java | [6 empty] | 永田 |  |  | 2023-06-19 | 2023-06-21 |  |  |  | 3 | [31 empty] | 80% | 80% | bar: 月 to 水
| 結合テスト | HomeServlet.java | [6 empty] | 斎藤 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 81% | 81% | bar: 月 to 火
|  | LoginServlet.java | [6 empty] | 永田 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 82% | 82% | bar: 月 to 火
|  | AccountServlet.java | [6 empty] | 永田 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 83% | 83% | bar: 月 to 火
|  | ScheduleServlet.java | [6 empty] | 鈴木 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 84% | 84% | bar: 月 to 火
|  | CalendarServlet.java | [6 empty] | 斎藤 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 85% | 85% | bar: 月 to 火
|  | GoalRegistServlet.java | [6 empty] | 篠崎 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 86% | 86% | bar: 月 to 火
|  | TaskRegistServlet.java | [6 empty] | 篠崎 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 87% | 87% | bar: 月 to 火
|  | AchieveServlet.java | [6 empty] | 斎藤 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 88% | 88% | bar: 月 to 火
|  | ExplanationServlet.java | [6 empty] | 永田 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 89% | 89% | bar: 月 to 火
|  | NextMonthServlet.java | [6 empty] | 斎藤 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 90% | 90% | bar: 月 to 火
|  | LastMonthServlet.java | [6 empty] | 斎藤 |  |  | 2023-06-26 | 2023-06-27 |  |  |  | 2 | [31 empty] | 91% | 91% | bar: 月 to 火
| 総合テスト | 全体の動作確認 | [9 empty] | 2023-06-27 | 2023-06-28 |  |  |  | 2 | [31 empty] | 92% | 92% | bar: 火 to 水
| 発表準備 | [10 empty] | 2023-06-19 | 2023-06-28 | [35 empty] | 93% | 93%
| 発表会 | [11 empty] | 2023-06-30 | [35 empty] | 94% | 94%
[17 empty] | 286 | [31 empty] | 95% | 95%
[49 empty] | 96% | 96%
[49 empty] | 97% | 97%
[49 empty] | 98% | 98%
[49 empty] | 99% | 99%

## 予実グラフ
| 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
進捗率 |  |  |  | 27.83% | 42.97% | 42.97% | 42.97% | 53.01% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
予定進捗率 | 10% | 20% | 30% | 35% | 40% | 50% | 50% | 50% | 60% | 70% | 80% | 100%
総工数 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286
当日工数 | 11 | 13 | 13 | 23 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
工数積算 | 木: 79.6; 金: 122.9; 土: 122.9; 日: 122.9; 月: 151.6
[5 empty] | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6 | 151.6
8
工数積算＝（（工数:人日）ｘ（各進捗率））ｘ全部
当日工数＝当日作業した工数
進捗率＝（工数積算）/（総工数）
予定進捗率＝予定されている進捗率
これにはテストや最終チェックの工数が入ってませんが
実際はテストなども入れた総工数で計算してください
工数積算は実際のみなさんの表から取り出して計算ください

## Sheet3
ファイル形式
Home.jsp | 1
Login.jsp | 1
Account.jsp | 1
Schedule.jsp | 2
Calendar.jsp | 2
GoalRegist.jsp | 2
TaskRegist.jsp | 2
Achieve.jsp | 2
Explanation.jsp | 1
TodoRejist.jsp | 2
AccountID.jsp | 1
IdpwDao.java | 1
DaysDao.java | 1
LgDao.java | 1
SgDao.java | 1
TodotbDao.java | 0.5
TasktbDao.java | 1
MemotbDao.java | 1
Idpw.java | 1
Days.java | 1
Lg.java | 1
Sg.java | 1
Todo.java | 1
Task.java | 1
Memo.java | 1
User.java | 1
Achieve.java | 1
Result.java | 1
HomeServlet.java | 0
LoginServlet.java | 3
AccountServlet.java | 3
ScheduleServlet.java | 3
CalendarServlet.java | 2.4
GoalRegistServlet.java | 3
TaskRegistServlet.java | 0
AchieveServlet.java | 1.5
ExplanationServlet.java | 3
NextMonthServlet.java | 4.8
LastMonthServlet.java | 4.8
common.js | 0
home.js | 0
login.js | 7
account.js | 7
schedule.js | 10
calendar.js | 0
goal_regist.js | 8
task_regist.js | 7
achieve.js | 0
explanation.js | 6.3
todo_regist.js | 7
common.css | 3.6
home.css | 5.6
login.css | 6
account.css | 6
schedule.css | 6.4
calendar.css | 4.9
goal_regist.css | 0
task_regist.css | 0
achieve.css | 0
todo_regist.css | 0
AccountID.css | 4.8
Home.jsp | 0
Login.jsp | 0
Account.jsp | 0
Schedule.jsp | 0
Calendar.jsp | 0
GoalRegist.jsp | 0
TaskRegist.jsp | 0
Achieve.jsp | 0
Explanation.jsp | 0
TodoRejist.jsp | 0
AccountID.jsp | 0
IdpwDao.java | 0
DaysDao.java | 0
LgDao.java | 0
SgDao.java | 0
TodotbDao.java | 0
TasktbDao.java | 0
MemotbDao.java | 0
HomeServlet.java | 0
LoginServlet.java | 0
AccountServlet.java | 0
ScheduleServlet.java | 0
CalendarServlet.java | 0
GoalRegistServlet.java | 0
TaskRegistServlet.java | 0
AchieveServlet.java | 0
ExplanationServlet.java | 0
NextMonthServlet.java | 0
LastMonthServlet.java | 0
全体の動作確認 | 0
151.6